## Workback Template
EVENT DATE: |  | 2016-01-01
Deadline | Days from event | Action | Responsibility | Assigned To | Status | Notes
2015-12-02 | -30 | Confirm date and booking with venue | Venue Liaison |  | Not Started
2015-12-07 | -25 | Respond (politely) to comments from Meetup and Eventbrite | Pre, During & Post-Event Social Media |  | Not Started
2015-12-07 | -25 | Email directors for speaker ideas | Speaker Planning, Selection & Management |  | Not Started
2015-12-07 | -25 | Email users on Meetup to let them know about the mailing list | Meetup/Eventbrite & Guest List |  | Not Started
2015-12-12 | -20 | Appeal for volunteers | Volunteer Recruitment & Management |  | Not Started
2015-12-12 | -20 | Review lightning pitch submission doc to check for new requests | Lightning Pitch Planning, Selection & Management |  | Not Started
2015-12-12 | -20 | Send out notification when event registration opens | Pre, During & Post-Event Social Media |  | Not Started
2015-12-12 | -13 | Tweet that second batch of tickets are available | Pre, During & Post-Event Social Media |  | Not Started
2015-12-12 | -20 | Increase paid ticket numbers in line with any paid ticket cancellations (ongoing until day of event) | Meetup/Eventbrite & Guest List |  | Not Started
2015-12-12 | -20 | Create event on Eventbrite, email out first batch of tickets | Meetup/Eventbrite & Guest List |  | Not Started
2015-12-12 | -20 | Sent out email notifying people that first batch of tickets are open | Meetup/Eventbrite & Guest List |  | Not Started
2015-12-17 | -15 | Contact community and directors for lightning pitches | Lightning Pitch Planning, Selection & Management |  | Not Started
2015-12-17 | -6 | Tweet that third batch of tickets are available | Pre, During & Post-Event Social Media |  | Not Started
2015-12-19 | -13 | Email out second batch of tickets | Meetup/Eventbrite & Guest List |  | Not Started
2015-12-22 | -10 | Send out notification when each speaker is secured. | Pre, During & Post-Event Social Media |  | Not Started
2015-12-22 | -10 | Book after-drinks venue | Drinks & Bar |  | Not Started
2015-12-22 | -10 | Find and confirm speakers | Speaker Planning, Selection & Management |  | Not Started
2015-12-25 | -7 | Find and confirm lightning pitches | Lightning Pitch Planning, Selection & Management |  | Not Started
2015-12-25 | -7 | Contact venue and liaise with AV specialists | AV Tech & Recording |  | Not Started
2015-12-25 | -7 | Liaise with venue re. security concerns | Venue Liaison |  | Not Started
2015-12-25 | -7 | Order drinks | Drinks & Bar |  | Not Started
2015-12-25 | -7 | Refund any paid tickets that have already been cancelled | Meetup/Eventbrite & Guest List |  | Not Started
2015-12-25 | -7 | Secure a sponsor | Fundraising and Sponsorship |  | Not Started
2015-12-25 | -7 | Add confirmed speakers, lightning pitches and sponsors | Meetup/Eventbrite & Guest List |  | Not Started
2015-12-25 | -7 | Email out third batch of tickets | Meetup/Eventbrite & Guest List |  | Not Started
2015-12-26 | -6 | Work with speaker and pitch managers to ensure we have permission to record | AV Tech & Recording |  | Not Started
2015-12-27 | -5 | Brief those doing lightning pitches | Lightning Pitch Planning, Selection & Management |  | Not Started
2015-12-27 | -5 | Brief volunteers | Volunteer Recruitment & Management |  | Not Started
2015-12-27 | -5 | Brief those speaking | Speaker Planning, Selection & Management |  | Not Started
2015-12-29 | -3 | Confirm volunteer names and numbers and inform guest-list manager | Volunteer Recruitment & Management |  | Not Started
2015-12-29 | -3 | Compile running order and distribute | Event Lead |  | Not Started
2015-12-29 | -3 | Get slides ahead of time | Speaker Planning, Selection & Management |  | Not Started
2016-01-01 | 0 | Organise pitches on the day | Lightning Pitch Planning, Selection & Management |  | Not Started
2016-01-01 | 0 | Assign them tasks on the day | Volunteer Recruitment & Management |  | Not Started
2016-01-01 | 0 | Send out notification when registration is closed | Pre, During & Post-Event Social Media |  | Not Started
2016-01-01 | 0 | Post and RT key quotes and links from speakers and lightning pitches during event (incl. Hashtag and speaker’s name) | Pre, During & Post-Event Social Media |  | Not Started
2016-01-01 | 0 | Ensure tech requirements are in place to record event | AV Tech & Recording |  | Not Started
2016-01-01 | 0 | Welcome and oversee speakers on the day (make sure they have a drink, etc) | Speaker Planning, Selection & Management |  | Not Started
2016-01-01 | 0 | Welcome and oversee sponsors on the day (make sure they have a drink, etc) | Fundraising and Sponsorship |  | Not Started
2016-01-01 | 0 | Compile final guest list by 2pm on the day of the event and send to Twitter | Meetup/Eventbrite & Guest List |  | Not Started
2016-01-02 | 1 | Thank speakers after the event on social media | Pre, During & Post-Event Social Media |  | Not Started
2016-01-02 | 1 | Send post-event thank you to speakers | Speaker Planning, Selection & Management |  | Not Started
2016-01-02 | 1 | Invoice sponsor | Fundraising and Sponsorship |  | Not Started
2016-01-02 | 1 | Send post-event thank you to sponsors | Fundraising and Sponsorship |  | Not Started
2016-01-02 | 1 | Refund any remaining cancelled tickets | Meetup/Eventbrite & Guest List |  | Not Started
2016-01-08 | 7 | Pay for drinks | Accounts & Invoicing |  | Not Started
2016-01-11 | 10 | Chase sponsor payment | Fundraising and Sponsorship |  | Not Started
Formulas:
Deadline = C1+[Days from event]
Deadline = C1+[Days from event, row above]

## Key
Not Started
In Progress
Complete